## Initiatives
ID | Initiative | Phase | Source_Framework | Department | Priority | Status | Completion_Pct | Start_Date | Target_Date | Owner
SI-001 | Expand Business Administration online offerings | Phase 2 | BCG / Gray Associates | Business | High | In Progress | 35 | 2025-09-01 | 2026-08-01 | Dean of Business
SI-002 | Launch Health Sciences graduate certificate | Phase 2 | Gray Associates | Health Sciences | High | Planning | 10 | 2025-11-01 | 2026-08-01 | Dean of Health Sciences
SI-003 | Restructure Environmental Science/Studies programs | Phase 2 | BCG / Gray Associates | Environment & Sustainability | High | In Progress | 25 | 2025-09-01 | 2026-12-01 | Provost
SI-004 | Develop AI Institute partnerships and curriculum | Phase 2 | PESTLE | Computer Science / AI | High | Planning | 15 | 2025-10-01 | 2027-01-01 | AI Institute Director
SI-005 | Create Engineering co-op/internship pipeline | Phase 2 | Porter's / Gray Associates | Engineering | Medium | Not Started | 0 | 2026-03-01 | 2026-12-01 | Dean of Engineering
SI-006 | Implement retention intervention for First-Gen students | Phase 2 | PESTLE / Institutional Data | Student Affairs | High | In Progress | 40 | 2025-08-01 | 2026-05-01 | VP Student Affairs
SI-007 | Review and consolidate low-enrollment humanities programs | Phase 2 | BCG / Gray Associates | Arts & Humanities | Medium | Planning | 10 | 2025-11-01 | 2026-12-01 | Provost
SI-008 | Expand dual enrollment feeder pipeline | Phase 2 | Institutional Data | Enrollment Management | Medium | In Progress | 30 | 2025-08-01 | 2026-08-01 | VP Enrollment
SI-009 | Develop outdoor recreation industry partnerships | Phase 2 | Porter's Five Forces | Adventure Education | Medium | Not Started | 0 | 2026-01-01 | 2026-08-01 | Dean of Education
SI-010 | Create data-driven advising system | Phase 2 | PESTLE / Institutional Data | Academic Affairs | High | Planning | 20 | 2025-10-01 | 2026-05-01 | Provost
SI-011 | Launch transfer-friendly marketing campaign | Phase 2 | Porter's Five Forces | Enrollment Management | Medium | In Progress | 45 | 2025-09-01 | 2026-03-01 | VP Enrollment
SI-012 | Pilot competency-based credentials in IT | Phase 2 | Gray Associates / Porter's | Computer Info Systems | Low | Not Started | 0 | 2026-06-01 | 2027-01-01 | Dept Chair CIS
SI-013 | Strengthen Native American student support services | Phase 2 | PESTLE / Mission | Student Affairs | High | In Progress | 50 | 2025-08-01 | 2026-08-01 | VP Student Affairs
SI-014 | Develop faculty recruitment incentive package | Phase 2 | Porter's Five Forces | Academic Affairs | Medium | Not Started | 0 | 2026-01-01 | 2026-08-01 | VP Academic Affairs
SI-015 | Establish program-level KPI dashboard | Phase 2 | All Frameworks | Provost Office | High | Planning | 15 | 2025-10-01 | 2026-03-01 | Provost

## Milestones
ID | Milestone | Target_Date | Status | Notes
MS-001 | Phase 1 Analysis Complete | 2025-12-15 | Complete | BCG, PESTLE, Porter's, Gray Associates analyses delivered
MS-002 | Board Presentation of Findings | 2026-01-20 | Complete | Presented to Board of Trustees at January retreat
MS-003 | Implementation Plans Approved | 2026-02-15 | In Progress | Department chairs reviewing implementation details
MS-004 | Q1 Progress Review | 2026-03-31 | Upcoming | Scheduled for March 31
MS-005 | Retention Intervention Pilot Launch | 2026-02-01 | In Progress | First-gen student cohort identified, mentors assigned
MS-006 | Online Program Proposal Submitted | 2026-03-01 | In Progress | Business Admin online MBA proposal in review
MS-007 | Dual Enrollment Partnerships Signed | 2026-04-15 | Not Started | Target: San Juan College, Pueblo CC, Red Rocks CC
MS-008 | Mid-Year Progress Report | 2026-06-30 | Upcoming | All initiatives report progress mid-year
MS-009 | Program Restructuring Plans Finalized | 2026-05-01 | Not Started | Environmental programs and humanities consolidation
MS-010 | Year 1 Implementation Review | 2026-08-15 | Upcoming | Full assessment of Year 1 outcomes

## KPIs
KPI | Category | Current_Value | Target_Value | Unit | Timeframe
Total Enrollment | Enrollment | 3457 | 3700 | students | Fall 2027
Retention Rate (FTFT) | Retention | 66.1 | 72 | % | Fall 2027
Graduate Enrollment | Enrollment | 160 | 200 | students | Fall 2027
First-Year Class Size | Enrollment | 777 | 850 | students | Fall 2027
Degrees Awarded | Outcomes | 489 | 525 | degrees | FY 2026-27
Student-Faculty Ratio | Efficiency | 15 | 14 | :1 | Fall 2027
Online Course Offerings | Growth | 25 | 60 | courses | Fall 2027
Dual Enrollment Students | Growth | 235 | 300 | students | Fall 2027
Transfer Students | Enrollment | 190 | 220 | students | Fall 2027
Program Completion Rate | Outcomes | 42 | 48 | % | FY 2026-27
First-Gen Retention Gap | Equity | 5.2 | 2 | pp | Fall 2027
Native American Retention | Equity | 61 | 68 | % | Fall 2027

## Resources
Category | Allocated_Budget | Spent_to_Date | Department
Faculty Hiring (STEM/Health) | 450000 | 120000 | Academic Affairs
Online Program Development | 300000 | 85000 | Academic Affairs
Student Support Services | 250000 | 150000 | Student Affairs
Technology Infrastructure | 200000 | 60000 | IT
Marketing & Recruitment | 350000 | 200000 | Enrollment Management
Dual Enrollment Expansion | 150000 | 45000 | Academic Affairs
Faculty Development | 100000 | 30000 | Provost Office
Data Analytics Platform | 125000 | 50000 | Institutional Research